WP 5–Managemant and coordination

DEV 5.2.–Quality Control and Monitoring

***-WP 1-***

Table of Contents

[1. Overview about WP implementation 3](#_Toc507420593)

[2. Conclusions/Suggestions 3](#_Toc507420594)

# 1. Overview about WP implementation

The general overview of implemented activities in WP1 is given in the table below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Activity** | **Deliverables** | | **Indicators** | |
| **DEV** | **Check** | **Indicator** | **Check** |
| Existing EU and global practices for cloud based solutions | (DEV) 1.1- Report “*Existing* *EU and global practices for cloud based solutions*”- M | √ | -Target value: 1 report  Achieved value: 1 report  -7 EU countries analyzed | √ |
| Review on cloud computing service related business objectives | (DEV) 1.2- Report “*Review* *on cloud computing service related business objectives*” | √ | -Target value: 1 report  Achieved value: 1 report | √ |
| Analyses of current practice in ICT development in ME | (DEV) 1.3- Report “*Analyses of current practice in ICT development in ME*” | √ | -Target value: 1 report  Achieved value: 1 report | √ |
| Regulatory Compliance with international experience | (DEV) 1.4- Report ”*Regulatory Compliance with international* *experience*” | √ | -Target value: 1 report  Achieved value: 1 report | √ |
| Raising awareness about cloud computing technologies and cloud based solutions | (DEV) 1.5- Reports on organized workshops and roundtables | √ | -Target value: 2 events Achieved value: 2 events  -Target value: 30 SMEs  Achieved value: 125 SMEs | √ |

# 2. Conclusions/Suggestions

Try to spread knowledge and raise awareness about cloud computng, among SMEs, especially smaller entreprieses.